## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-03-26 |  |  |  |  | March | [6 empty] | April | [27 empty] | May
Scrolling Increment: | 1 | time axis 2022-03-27 to 2022-05-21
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-03-27 to 2022-05-21
TITLE 1
Task 1 | Goal | Name | 25% | 2022-03-26 | 3 | 2022-03-27: 2; 2022-03-28: 2
Task 2 | Milestone |  |  | 2022-03-31 | 1 | bar: 2022-03-31
Task 3 | Low Risk |  | 50% | 2022-03-23 | 10
Task 4 | Milestone |  |  | 2022-04-15 | 1 | bar: 2022-04-15
Task 5 | Med Risk |  | 10% | 2022-04-01 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-04-01 | 13
Task 2 | On Track |  | 50% | 2022-04-03 | 9
Task 3 | Low Risk |  | 33% | 2022-04-08 | 11
Task 4 | Milestone |  |  | 2022-04-10 | 1 | bar: 2022-04-10
Task 5 |  |  |  | 2022-04-11 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-04-10 | 4
Task 2 | Med Risk |  |  | 2022-04-13 | 14
Task 3 | On Track |  |  | 2022-04-28 | 6
Task 4 | Goal |  |  | 2022-05-02 | 3 | 2022-05-02: 2; 2022-05-03: 2; 2022-05-04: 2
Task 5 | Low Risk |  |  | 2022-04-01 | 19
TITLE 4
Task 1 |  |  |  | 2022-05-05 | 15
Task 2 |  |  |  | 2022-05-19 | 5
Task 3 | Milestone |  |  | 2022-06-30 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PyUnitTest
CIS 565 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Austin Davis, Austin Horton and Mayank Waghmare
Project Start Date: | 2022-02-05 |  |  |  |  | February | [27 empty] | March
Scrolling Increment: | 0 | time axis 2022-02-05 to 2022-04-01
Milestone description | Category | Assigned to | Progress | Start | Days | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Phase 1: Project Identification/Description
Project Proposal | On Track | Austin Davis | 100% | 2022-02-05 | 4
Phase 1 Complete | Milestone |  | 100% | 2022-02-09 | 1
Phase 2: Requirements/Design
Requirements Elicitation | On Track | Austin Davis | 100% | 2022-02-09 | 4
Research | Low Risk | Austin Davis, Austin Horton, Mayank Waghmare | 85% | 2022-02-13 | 45
Software Architecture Design | Med Risk | Austin Davis, Austin Horton, Mayank Waghmare | 75% | 2022-03-03 | 27
Phase 2 Presentation | On Track | Austin Davis, Austin Horton, Mayank Waghmare | 0% | 2022-03-25 | 5
Phase 2 Complete | Milestone |  | 0% | 2022-03-30 | 1 | bar: W
Phase 3: Coding
AST parsing | On Track | Austin Davis | 100% | 2022-03-08 | 14
Setup functions | High Risk | Mayank Waghmare | 0% | 2022-03-08 | 10
Teardown functions | High Risk | Mayank Waghmare | 0% | 2022-03-22 | 11
Main PyUnitTest class | High Risk | Austin Davis | 0% | 2022-03-21 | 9
Assertions | High Risk | Austin Horton | 0% | 2022-03-08 | 14
Test Case/Results | High Risk | Austin Horton | 0% | 2022-03-08 | 14
Phase 3 Complete | Milestone |  | 0% | 2022-04-10 | 1
Phase 4: Evaluation
Testing | On Track | Austin Davis | 0% | 2022-04-01 | 9
Phase 4 Complete | Milestone |  | 0% | 2022-04-10 | 1
Phase 5: Presentation/Report
Report | On Track | Austin Davis, Austin Horton, Mayank Waghmare | 0% | 2022-04-11 | 4
Presentation | On Track | Austin Davis, Austin Horton, Mayank Waghmare | 0% | 2022-04-16 | 6
Phase 5 Complete | Milestone |  | 0% | 2022-04-22 | 1
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-03-26 |  |  |  |  | March | [6 empty] | April | [27 empty] | May
Scrolling Increment: | 5 | time axis 2022-03-31 to 2022-05-25
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-03-31 to 2022-05-25
TITLE 1
Task 1 | Goal | Name | 25% | 2022-03-26 | 3
Task 2 | Milestone |  |  | 2022-03-31 | 1 | bar: 2022-03-31
Task 3 | Low Risk |  | 50% | 2022-03-23 | 10
Task 4 | Milestone |  |  | 2022-04-15 | 1 | bar: 2022-04-15
Task 5 | Med Risk |  | 10% | 2022-04-01 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-04-01 | 13
Task 2 | On Track |  | 50% | 2022-04-03 | 9
Task 3 | Low Risk |  | 33% | 2022-04-08 | 11
Task 4 | Milestone |  |  | 2022-04-10 | 1 | bar: 2022-04-10
Task 5 |  |  |  | 2022-04-11 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-04-10 | 4
Task 2 | Med Risk |  |  | 2022-04-13 | 14
Task 3 | On Track |  |  | 2022-04-28 | 6
Task 4 | Goal |  |  | 2022-05-02 | 3 | 2022-05-02: 2; 2022-05-03: 2; 2022-05-04: 2
Task 5 | Low Risk |  |  | 2022-04-01 | 19
TITLE 4
Task 1 |  |  |  | 2022-05-05 | 15
Task 2 |  |  |  | 2022-05-19 | 5
Task 3 | Milestone |  |  | 2022-06-30 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one